|  |
| --- |
| **Description of the implemented and planned activities** |

|  |  |  |  |
| --- | --- | --- | --- |
| **WP1-Preparation** | | | |
| **Activity Title** | **Start date** | **End date** | **Status of the activity** |
| 1.1 Quantitative analysis of teaching competences of young, newly hired university teachers at the PC HEIs; | January 2019 | July, 2019 | **COMPLETED** |
| 1.2 Detailed analysis of the use of modern educational technologies in T&L at the PC HEIs; | January 2019 | July, 2019 | **COMPLETED** |
| 1.3 Reviewing experiences in the use of PMT in T&L at the EU HEIs | March 2019 | May, 2019 | **COMPLETED** |
| 1.4 Performing a comparative analysis based on collected data; | March 2019 | November,.2019 | **COMPLETED** |
| 1.5 Defining necessary measures and actions for the modernisation of T&L | November.2019 | January, 2020 | **COMPLETED** |
| **WP2-**  **Upgrading educational infrastructure at the PC HEIs** | | | |
| **Activity Title** | **Start date** | **End date** | **Status of the activity** |
| 2.1 Forming technology-enhanced learning spaces | April 2019 | January, 2020 | **COMPLETED** |
| 2.2 Preparing material for PPM training courses | March 2020  postponed |  | **ONGOING ACTIVITY** |
| 2.3 Creating material for providing language support for teaching staff | March 2020  postponed |  | **ONGOING ACTIVITY** |
| 2.4 Preparing guidelines for the technological enhancement of teaching and learning | May 2020  postponed |  | **ONGOING ACTIVITY** |

|  |  |  |  |
| --- | --- | --- | --- |
| **WP3- Professional development of teaching staff** | | | |
| **Activity Title** | **Start date** | **End date** | **Status of the activity** |
| 3.1 Organising the Workshop on innovative methodologies and pedagogical approaches | September 2020,  postponed |  | **SHOULD BE REALISED** |
| 3.2 PM training of teaching staff | October 2020,  postponed | End of the project | **SHOULD BE REALISED** |
| 3.3 Training of teaching staff for using new educational technologies | October 2020,  postponed | End of the project | **SHOULD BE REALISED** |
| 3.4 Training for teaching and academic writing in English | postponed | End of the project | **SHOULD BE REALISED** |
| 3.5 Development of structure and contents of courses for students and young teachers |  |  | **ONGOING ACTIVITY** |
| **WP4- Professional development of teaching staff** | | | |
| 4.1 The integration of online technologies into traditional courses | March 2020, implemented preterm by force of circumstances | | **ONGOING ACTIVITY** |
| **WP5 - Quality assurance and monitoring** | | | |
| The first tree activities and deliverables of the WP 5 were largerly completed before March 2020 in accordance with the project application plan and schedule. There have been some time shifts in project implementation in relation to the period that was foreseen for certain activities in the project plan. The internal quality standards are established. The outcomes are not achieved on time because of these unpredicted and extraordinary circumstances and we have to prepare a report that will show the issues related to project quality and possibilities for re-arranging and re-defining the planned activities. | | | |